## List1
| #1 | #2 | #3 | #4 | #5 | #6
| iOS | iOS | iOS | Android | Android | Android
iOS development | 1 | 2 | 4 | 1 | 1 | 1
xCode | 2 | 3 | 4 | 1 | 1 | 1
Android development | 1 | 2 | 2 | 3 | 2 | 3
Android Studio | 4 | 4 | 2 | 4 | 3 | 5
SCRUM | 3 | 1 | 1 | 1 | 1 | 4
SPL | 2 | 2 | 1 | 2 | 2 | 1
Experiebnces in mobile dev | 2 | 2.5 | 5.4 | 4 | 3.5 | 4.5
hours per day | 10 | 7 | 10 | 8 | 8 | 10
SPL | 3 | 3 | 2 | 4 | 2 | 3
afraid to change | 3 | 3 | 4 | 3 | 1 | 1
organisational work % | 65 | 20 | 20 | 30 | 30 | 20
What to improve? | Changing requirements | More precise requirements | More precise requirements | Better product roadmap | more productive meetings, better defined requirements
more incremental development
positive - tech | new production experience (iOS) | production (iOS) | gained experience | multiedition development | new experiences | demo edition developped and released in 3 hours
SCRUM
positive - organizational | SCRUM method | SCRUM method | SCRUM | Scrum | groupwork, SCRUM
negative - tech | approach for multiedition management | usniog emulator instead of real phone | development cadence was to high | bad requirements -> unnecessary rework
Changing already developed functionalities
negative - organizational | more time for objective C in details | more time for QA, better defined requirements | better communication with client | 40-hour week was an utopia
technical changes | several smaller apps, not one huge | development on physical devices | to many functionalities in one app | using latest Android, GIT instead of SVN, better gub reporting and progress tracking
organizational changes | #2: more time for studying requirements; #4: shorter workday, more time for prototyping; #5: better coworking from the beginning
important experiences | production development | SCRUM, iOS |  | production dev, good design, scrum, team work issues | teamwork, self-organizing team